## Mobile
Sr No | Item | Expected date of completion | Status
1 | Wire frame | 2016-08-03 | In Progress
2 | HTML Mockup with navigations | 2016-10-03 | In Progress
3 | Mobile Framework with project | 2016-11-03
4 | Splash screen | 2016-11-03
5 | upload CSV of contacts | 2016-11-03 | Not required
6 | My Connections page | On the day
7 | Techno-digital Profile | On the day
8 | History page | On the day
9 | Settings page | On the day
10 | code integration | On the day
11 | deployment of apk | On the day

## Web App
Sr No | Item | Expected date of completion | status
1 | Wire frame | 2016-08-03 | Done
2 | HTML Mockup with navigations | 2016-10-03 | In Progress
3 | Web and API Framework | 2016-10-03 | In Progress | keshav
4 | Integration of HTML with framework | 2016-11-03 | In Progress | sadhvi
5 | Push notification setup | 2016-12-03 | ?? | eric
6 | Dashboard screen ((actual screens dummy) | 13/3/2016 |  | sadhvi
7 | Campaign Page (actual screens dummy) | On the day
8 | Techno Digital Page (actual screens dummy) | On the day
9 | Pending Actions (actual screens dummy) | On the day
10 | API for uploading contacts | 2016-10-03 | Not required
11 | API for saving tags (part of settings) | 2016-10-03 | Not required
12 | API for showing candidate history (timeline) | On the day
13 | API for Jobs page GET | On the day
14 | API for Referal page confirm Jobs POST | On the day
15 | API for Getting connections GET | On the day
16 | Login API | On the day
17 | Job to match connects with jobs | 2016-12-03
18 | Sent notification to the user | 2016-12-03
19 | Integration of Dashboard screen Actual Data | On the day
20 | Integration of Campaign page Actual Data | On the day
21 | Techno Digital Page Actual Data | On the day
22 | Job Listing Analytics Actual Data | On the day
23 | Logic to update campaign page | On the day
24 | Integration with gituhub API | 2016-12-03 | In Progress | Rajat
25 | Integration with stackoverflow API | 2016-12-03 | In Progress | Rajat
26 | Logic to update the effectiveness matrix | On the day
27 | API for profile details GET
28 | API for profile details POST

## Database Design
Sr No | Item | Expected date of completion | Status
1 | Database Design | 2016-07-03 | Done
2 | System Setup | 2016-08-03 | In Progress