## Mobile
Sr No | Item | Expected date of completion | Status
1 | Wire frame | 2016-08-03 | In Progress
2 | HTML Mockup with navigations | 2016-10-03 | In Progress
3 | Mobile Framework with project | 2016-11-03
4 | Splash screen | 2016-11-03
5 | upload CSV of contacts | 2016-11-03 | Not required
6 | My Connections page | On the day | Megha
7 | Techno-digital Profile | On the day | Rajat
8 | timeline page | On the day | Eric
9 | Sync page | On the day | Pranav
10 | code integration | On the day | Eric
11 | deployment of apk | On the day
12 | Jobs Page | On the day | Eric
13 | Jobs Details | On the day | Rajat
14 | My Referals | On the day | Megha

## Web App
Sr No | Item | Expected date of completion | status | Type of task
1 | Wire frame | 2016-08-03 | Done
2 | HTML Mockup with navigations | 2016-10-03 | In Progress
3 | Web and API Framework | 2016-10-03 | In Progress |  | keshav
4 | Integration of HTML with framework | 2016-11-03 | In Progress |  | sadhvi
5 | Push notification setup | 2016-12-03 | ?? |  | eric
6 | Dashboard screen ((actual screens dummy) | 13/3/2016 |  | Screen | Richa
7 | Campaign Page (actual screens dummy) | On the day |  | Screen | Sadhvi
8 | Techno Digital Page (actual screens dummy) | On the day |  | Screen | Sadhvi
9 | Pending Actions (actual screens dummy) | On the day |  | Screen | Richa
10 | API for uploading contacts | 2016-10-03 | Not required
11 | API for saving tags (part of settings) | 2016-10-03 | Not required
12 | API for showing candidate history (timeline) | On the day |  | API | keshav | Collection referral_history
13 | API for Jobs page GET | On the day |  | API | keshav | Collection campaign_referral and campaign
14 | API for Referal page confirm Jobs POST | On the day |  | API | Nitin | Collection campaign_referral and referral_history
15 | API for Getting connections GET | On the day |  | API | Nitin | Collection user_connections
16 | Login API | On the day |  | API
17 | Job to match connects with jobs | 2016-12-03 |  |  | Keshav
18 | Sent notification to the user | 2016-12-03
19 | Integration of Dashboard screen Actual Data | On the day
20 | Integration of Campaign page Actual Data | On the day
21 | Techno Digital Page Actual Data | On the day
22 | Job Listing Analytics Actual Data | On the day
23 | Logic to update campaign page | On the day
24 | Integration with gituhub API | 2016-12-03 | In Progress |  | Rajat
25 | Integration with stackoverflow API | 2016-12-03 | In Progress |  | Rajat
26 | Logic to update the effectiveness matrix | On the day
27 | API for profile details GET |  |  | API | Keshav | Collection user_connections
28 | API for profile details POST |  |  | API | Nitin | Collection user_connections
29 | Login Page

## Database Design
Sr No | Item | Expected date of completion | Status
1 | Database Design | 2016-07-03 | Done
2 | System Setup | 2016-08-03 | In Progress